## 00_README
FLUENTWAVE BUILD CONTROL WORKBOOK V1
Purpose | Single execution state for the MVP vertical slice.
Rule | Update status/evidence before adding scope.
15% rule | Every iteration must produce measurable progress in one phase.
Gate | P1–P4 are P0; P5 follows the event model.
Pyramid | Evidence score, not marketing language.
Source limitation | Previously uploaded files are expired/unavailable in this session; this workbook uses retained project context. Re-upload source files for source-grounded reconciliation.

## 01_Control_Tower
Phase | Status | Completion % | Priority | Pyramid /5 | Gate | Next 15% Move | Owner | Evidence
P1 Readiness | IN PROGRESS | 35 | P0 | 2.5 | HOLD | Run 5–10 real assessments; lock rubric/scoring/tests | Product/AI | Cases + scoring
P2 Documents | DEFINED / EARLY BUILD | 25 | P0 | 2.5 | HOLD | Run 5 mobile document sets; measure errors | Fullstack/DevOps | Document cases
P3 Human Review | DEFINED | 20 | P0 | 2 | HOLD | Reviewer queue + reason codes + audit events | Ops | Review log
P4 Routing | DEFINED / LIVE MANUAL | 30 | P0 | 2.5 | HOLD | Partner registry + attribution + handoff packet | Founder/Ops | Routed cases
P5 Dashboard | ARCHITECTED | 15 | P1 | 1.5 | HOLD | Event-driven timeline + next action | Fullstack | Usability tests

## 02_Phase_Stage_Matrix
Builder Stage | P1 Assessment | P2 Documents | P3 Review | P4 Routing | P5 Dashboard
Vision | Readiness outcome | Evidence outcome | Review outcome | Routing outcome | Visibility outcome
Research | Student/assessment evidence | Document burden/errors | Exceptions/reviewer needs | Partner requirements | Status/navigation needs
Domain Model | Profile, assessment, score | Document, checklist, evidence | Review, decision, reason | Partner, referral, attribution | Case, event, notification
PRD | Rules + acceptance | Rules + acceptance | Rules + acceptance | Rules + acceptance | Rules + acceptance
Architecture | Assessment service | Storage/OCR pipeline | Review queue | Routing service | Event-driven dashboard
Manual Pilot | 5–10 assessments | 5 document sets | Real exceptions | Real handoffs | Observe 5 users
Software | Stable automation | Stable automation | Stable automation | Stable automation | State display
AI Agents | Score/explain | Extract/classify | Prioritize/escalate | Recommend/match | Status assistance
Operations | Rubric + QA | Checklist + QA | Reviewer SOP | Partner SLA + attribution | Support SOP
Evidence | Accuracy/conversion | Completion/error rate | Review time/error | Routing/conversion | Activation/support reduction

## 03_Pyramid
Dimension | Threshold | P1 | P2 | P3 | P4 | P5 | Evidence
Problem | 4 | 4 | 4 | 4 | 4 | 4 | Recurring acute pain
Workflow | 4 | 3 | 3 | 3 | 3 | 2 | Repeatable flow
Data | 3 | 2 | 2 | 2 | 2 | 1 | Structured records
Automation | 4 | 1 | 1 | 1 | 1 | 0 | Reliable automation
Human QA | 4 | 4 | 4 | 4 | 4 | 3 | Controlled review/override
Economics | 3 | 2 | 2 | 2 | 2 | 1 | Cost/value signal
Trust & Compliance | 4 | 3 | 3 | 3 | 3 | 2 | Permissions/consent/audit
Distribution | 3 | 3 | 3 | 3 | 3 | 2 | Referral/acquisition
Retention | 3 | 1 | 1 | 1 | 1 | 0 | Continued use
Moat | 0 | 0 | 0 | 0 | 0 | 0 | Track accumulated advantage

## 04_Next_15pct
Priority | Phase | Action | Builder Stage | Lift | Dependency | Proof
P0 | P1 | Lock bilingual rubric + scoring + errors | 3–4 | +15% | Real assessments | 5–10 assessments
P0 | P2 | Mobile upload + checklist states | 4–6 | +15% | P1 profile | 5 document sets
P0 | P3 | Review queue + reasons + audit | 5–6 | +15% | P2 cases | 10 decisions
P0 | P4 | Partner registry + attribution | 3–5 | +15% | Partner records | 3 routed cases
P1 | P5 | Student timeline + next action | 5–7 | +15% | Event model | 5 usability tests
P1 | Cross-cutting | Confidence routing + escalation | 8 | +15% | Acceptance tests | 50 AI decisions
P1 | Cross-cutting | Knowledge base from exceptions | 9 | Continuous | Operational logs | 20 entries

## 05_State_Machines
Entity | State | Allowed Next State | Evidence/Event
Student | LEAD | INTAKE | Lead captured
Student | INTAKE | ASSESSMENT / WITHDRAWN | Intake submitted
Student | ASSESSMENT | DOCS_PENDING / ESCALATED | Score recorded
Student | DOCS_PENDING | DOCS_REVIEW | Required files uploaded
Student | DOCS_REVIEW | HUMAN_REVIEW / NEEDS_CORRECTION | Completeness result
Student | HUMAN_REVIEW | APPROVED / NEEDS_CORRECTION / REJECTED / ESCALATED | Reviewer decision
Student | APPROVED | ROUTED | Consent + eligibility
Student | ROUTED | APPLICATION_ACTIVE / WITHDRAWN | Partner acknowledgement
Document | REQUESTED | UPLOADED | File received
Document | UPLOADED | EXTRACTION_PENDING | Upload event
Document | EXTRACTION_PENDING | EXTRACTED / FAILED | OCR result
Document | EXTRACTED | VALIDATION_PENDING | Fields extracted
Document | VALIDATION_PENDING | VERIFIED / NEEDS_CORRECTION / REJECTED | Validation decision
Referral | CREATED | ATTRIBUTED | Referral ID
Referral | ATTRIBUTED | QUALIFIED | Eligibility
Referral | QUALIFIED | ROUTED | Partner match
Referral | ROUTED | APPLICATION_STARTED | Partner acknowledgement
Referral | APPLICATION_STARTED | ADMITTED / REJECTED | Institution decision
Referral | ADMITTED | ENROLLED / WITHDRAWN | Enrollment evidence
Referral | ENROLLED | COMMISSION_ELIGIBLE | Trigger satisfied
Referral | COMMISSION_ELIGIBLE | COMMISSION_PAID / DISPUTED | Payment evidence

## 06_Error_Recovery
Class | Example | Auto Response | Human Response | Recovery Evidence
Identity | Name mismatch | Block risky transition | Verify source | Verified identity
Document | Unreadable | Request retake | Review borderline | Readable file
Missing | Required doc absent | Task/reminder | Approve exception/request | Resolved checklist
Eligibility | Unclear rule | No auto approval | Counselor/partner review | Decision
AI confidence | <0.75 | Escalate | Human decision | Decision + rationale
Partner | No acknowledgement | SLA reminder | Re-route if breach | Partner event
Commission | Trigger disputed | Freeze payout | Review attribution/agreement | Resolution
Security | Unauthorized access | Deny + log | Investigate | Audit record

## 07_Acceptance_Tests
ID | Phase | Test | Pass Condition | Status | Evidence
P1-01 | P1 | Complete bilingual assessment | Fields + score stored | NOT STARTED
P1-02 | P1 | Low-confidence assessment | Review task created | NOT STARTED
P2-01 | P2 | Upload from phone | File + state stored | NOT STARTED
P2-02 | P2 | Missing document | Next action shown | NOT STARTED
P3-01 | P3 | Request correction | Reason + event stored | NOT STARTED
P4-01 | P4 | Route qualified case | Attributed handoff received | NOT STARTED
P4-02 | P4 | Duplicate referral | Conflict flagged | NOT STARTED
P5-01 | P5 | View status | State + next action visible | NOT STARTED
SEC-01 | All | Cross-tenant access | Denied + logged | NOT STARTED
AI-01 | All | Below-threshold AI | Escalates | NOT STARTED